## Bug_issue
Project Name | ishsan599 ¦ Figma |  | Issue Start Date | 2025-05-26 | Test Result: | Fixed | Not Fixed | In Progress |  | Bugs | 🐞 Bug remain Rate: 35.71% |  | Severity for Critical: 3.57%
Operation System | Android |  | Issue End Date | On-going |  | 18 | 10 | 0 |  |  |  |  | Severity for Major: 28.57%
Device Name | realme c17, emmulator: Pixel 9 Pro API 36 |  | Test Case Developed By | Md Abdur Rahaman Tutul | [6 empty] | ✅ Bug Fix Rate: 64.29% |  | Severity for Average: 42.86%
Sprint | - |  | Developer and Reviewed By | Nahid Hassan and Tohidul Islam | Total: | 28 |  |  |  |  | 🛠️ In Progress Rate: 0.00% |  | Severity for Minor: 25.00%
Bug ID | Module | Feature | Bug Type | Bug Title | Bug Description | Steps to Reproduce | Actual Result | Expected Result | Issue Labels | Severity | Attatchment | Dev_Status | Testers | Remark | Date and Time
Bug_ID_001 | Onbording Screen | Slider (Next/Skip Interface) | UI | Header displays fixed image instead of live status info | The header section uses a static image from Figma that includes a fixed date, network, Wi-Fi, and battery icon, which does not reflect real-time device status. | 1. Install and launch the ihsan599 mobile app. 2. Observe the header section on the onboarding screens. 3. Check the displayed date, network, Wi-Fi, and battery indicators. | Not as expected | The header should dynamically reflect the device’s current date, network status, Wi-Fi connection, and battery level. | Bug_Fixed | Minor | Video Link | Fixed | Tutul
Bug_ID_002 | Register/SignUp | Interests & Preferences | Functional | Missing Validation Message on Interest Selection | No validation message appears when user attempts to continue without selecting interests | 1. Open the app and complete registration 2. Navigate to the Interests & Preferences screen 3. Click "Save and Continue" without selecting any interests | Button does nothing, and no validation message appears | A validation message should inform the user to select at least one interest before proceeding | Improvements | Average | video link | Not Fixed
Bug_ID_003 |  | New User attempt | Functional | Type Error: _Map<String, dynamic> is not a subtype of String | New user tries to sign up, the app crashes or shows an error | 1. Open the app 2. Navigate to the Register tab 3. Fill in the registration fields 4. Tap on the "Register" button | app displays an error: type '_Map<String, dynamic>' is not a subtype of type 'String' | User should be registered successfully, or proper validation errors should be shown if inputs are incorrect. | Bug_Fixed | Major | Screen shot 1 Screen shot 2 | Not Fixed |  | Likely caused by passing a full JSON object (Map) instead of a specific string field (e.g. map['name']) where a String is expected. | 2025-07-30
Bug_ID_004 |  | Name input field | Functional | Name field lacks validation error on invalid input during sign up | The Name input field in the Sign Up screen does not show any validation error message when invalid or blank input is provided. | 1. Open the "ihsan599" mobile application. 2. Navigate to the Sign Up screen. 3. Enter an invalid value (e.g., numbers, symbols, or leave it blank) in the Name input field. 4. Enter valid email and password. 5. Tap on the Sign Up button. | Not as expected | A proper validation error message | Bug_Fixed | Average | Video Link | Fixed
Bug_ID_005 |  | Email input | Functional | No validation for existing email during signup | The system allows the user to register with an already registered email without showing any validation or error message. | 1. Open the ihsan599 mobile app. 2. Navigate to the Signup/Register tab. 3. Enter a name, password, and an email address that has already been registered. 4. Click on the Register button. | Not as expected | The system should validate the email and show a message like "Email already registered. Please use a different email or login | Bug_Fixed | Major | Screen shot | Fixed
Bug_ID_006 |  | Signup Screen | UI | Signup screen logo and "Login" link not fully visible without scrolling | The company logo and the "Already have account? Login" link are partially hidden on the signup screen and require scrolling to be seen. | 1. Open the Ihsan599 mobile application. 2. Navigate to the Signup/Register screen. 3. Observe the visibility of the company logo and the "Login" link at the bottom. 4. Same as "Login" tab | Not as expected | The application should be responsive for any android device | Bug_Fixed | Minor | Video Link | Fixed
Bug_ID_007 |  | "login" Link | Functional | Login link not clickable on Register page | The "Login" link on the Register page does not redirect to the Login screen when tapped | 1. Open the ihsan599 mobile application. 2. Navigate to the "Register" tab 3. Tap on the already have an accout "Login" link | Not as expected | Tapping the "Login" link should redirect the user to the Login screen. | Bug_Fixed | Average | Screen shot | Fixed
Bug_ID_008 | Login | Login Authentication | Functional | Server error occurs when user tries to log in with valid credentials | Users are unable to log in despite using correct credentials; a server error is displayed. | 1. Navigate to the login screen. 2. Enter valid username and password. 3. Tap on the "Login" button. | Server error message appears and login fails. | User should be successfully logged in and redirected to the dashboard/home screen. | Bug_Fixed | Major | Video Link | Fixed
Bug_ID_009 | Home, My Topics, Trends, Bookmark | Search Function | Functional | Search not working | Search input is inactive; checkable and checked set to false | 1. Go to Home, Treds, My Topics, Bookmark 2. Tap on search input or icon 3. Try to search | Nothing happens, no redirect or search triggered | Should redirect to results or show filtered content | Bug | Average | Video Link | Not Fixed |  | Likely search icon or input action not wired properly
Bug_ID_010 | My Topics | Header Title | UI | Incorrect Header Label After Selecting Recommendation Card | After navigating from "My Topics" in the footer and selecting a recommendation card, the header displays "Trending Now" instead of "Recommendation". | 1. Open the application (ihsan599). 2. Scroll to the footer and click on the "My Topics" menu. 3. You are redirected to a page with a tab containing recommendation cards. 4. Click/select any of the recommendation cards. 5.Observe the header in the next tab. | The header displays "Trending Now". | The header should display "Recommendation" to reflect the context of the user's action. | Bug | Average | Video Link | Fixed |  |  | 2025-06-02
Bug_ID_011 |  | Catagory titile padding | Functional | Improper Padding for Category Title | “Trending Now” tab does not have proper padding | 1. Go to footer and click on "My Topics" 2. navigate to Recommendations tab 3. Select any card 4. Observe the padding(e.g., entertaiment) | The category title appears cramped or misaligned due to insufficient padding. | The category title should have proper padding to align well | Bug | Minor | Screen Shot | Fixed |  |  | 2025-06-03
Bug_ID_012 |  | Trending Now> Header | Functional | Bookmark and Send button not working | Bookmark and Send icons are visible but have no action or response on tap | 1. Go to My Trend tab 2. Tap any trend card 3. On detail page, tap Bookmark or Send icon | Buttons have no action/response | Bookmark should save post, Send should trigger share/chat | Bug | Minor | Screen Shot | Not Fixed
Bug_ID_013 | Home | Header greating | Functional | Username not displayed | The header shows "Welcome Loading..." instead of the logged-in username. | 1. Login 2. Navigate to Home tab | Shows "Welcome Loading..." | Should show "Welcome [username]" | Bug_Fixed | Average | Video Link | Fixed |  | Likely username not fetched before UI loads
Bug_ID_014 |  | Header> Notification | Functional | Settings Icon Not Working | Clicking the settings icon in the notification tab has no effect | 1. Open the ihsan599 application 2. Navigate to the Home Page 3. Click the Notification Icon in the Header 4. On the Notification Tab, click the Settings Icon in the header | No action is triggered, no redirect or response | Settings icon should either open a settings view/modal or redirect to a relevant settings page | Bug | Major | Video Link | Fixed
Bug_ID_015 | Community Hub Tab | Back (<--) button | Functional | Back button not working | The back button in the header does not perform any action when clicked. | 1. Open app 2. Go to Community Hub tab 3. Tap on the back button in header | No action is triggered | Should navigate to the previous screen | Improvements | Minor | Video Link | Fixed |  | Possibly missing or broken onTap/Navigator.pop() logic
Bug_ID_016 |  | Filter Functionality | Functional | Filter functionality not implemented | Filter options (radio buttons & search by word) do not return or redirect to filtered results | 1. Go to Community Hub 2. Tap filter icon 3. Select filter or enter search 4. Tap Apply | No action or change on screen after applying filter or search | Should display filtered or searched results based on criteria | Bug | Average | Screen Shot | Fixed
Bug_ID_017 |  | Post Details View | Functional | Report button not working | Report (!) buttons on comment section don’t perform any action when tapped | 1. Go to Community tab 2. Open a post 3. Scroll to comments 4. Warning button on any comment | No action or feedback on button click | Like should increase count; Warning should trigger report action | Bug_Fixed | Average | Video link | Fixed |  | 29
Bug_ID_018 |  |  | Functional | Like button not working | Like buttons on comment section don’t perform any action when tapped | 1. Go to Community tab 2. Open a post 3. Scroll to comments 4. Tap Like button on any comment | No action or feedback on button click | Like should increase count | Bug | Major | Video link | Fixed
Bug_ID_019 |  |  | Functional | Bookmark and Send button not working | Bookmark and Send icons are visible but have no action or response on tap | 1. Go to Community tab 2. Tap any post card 3. On detail page, tap Bookmark or Send icon | Buttons have no action/response | Bookmark should save post, Send should trigger share/chat | Bug | Average | Video link | Not Fixed
Bug_ID_020 |  | Add New Post | Functional | Multiple posts on repeated clicks | Submitting a post multiple times by repeatedly clicking "Post" creates duplicate entries. | 1. Go to Community tab 2. Click "My Post" 3. Select "Add New Post" 4. Fill all fields 5. Click "Post" button multiple times rapidly | Same post gets submitted and displayed multiple times | Only one post should be submitted regardless of clicks | Bug | Average | Video link | Fixed |  | Add button disabling or loading state to prevent spam clicks
Bug_ID_021 |  | Post Comments | Functional | Delete Icon Not Working for Comments | Logged-in users cannot delete their own comments; delete icon appears but doesn't respond. | 1. Go to Community tab 2. Click any post 3. Add a comment 4. Tap the delete icon beside your comment | Delete icon does nothing | Comment should be deleted immediately or show confirmation | Bug_Fixed | Major | Video link | Fixed
Bug_ID_022 |  | Add New Post> Post details | Functional | Default Picture Added to Post Without User Input | After creating a new post, a default picture is automatically added even if the user doesn’t upload any image. | 1. On the redirected page, click “Add New Post.” 2. Fill in the form with Title, Topic, Category, and Post Content. 3. Submit the form without attaching an image. 4. After submission, observe the post details page. | The post shows a default image even though no image was uploaded by the user. | No image should be displayed unless the user explicitly uploads one. | Bug | Average | Video link | Fixed
Bug_ID_023 | Bookmark Tab | Contect Image | Functional | Bookmark tab not showing images | Image content inside content cards is not displaying in the bookmark tab | 1. Open app 2. Tap on Bookmark icon on Home header 3. View the opened tab | Should display filtered or searched results based on criteria | Cards should display corresponding images | Bug | Minor | Screen Shot | Not Fixed |  | 7
Bug_ID_024 |  | Treading and Posts >cards | Functional | Cards not clickable and not redirect any action in bookmark tab | Trending Now & Posts cards appear, but tapping them does nothing | 1. Open app 2. Tap bookmark icon on header 3. In "Trending Now" or "Posts", tap any card | Card tap does nothing | Card should open details or redirect to related screen | Bug | Major | Video Link | Not Fixed |  |  | 2025-06-02
Bug_ID_025 |  | Recommendation Topics> card | Functional | Redirects entire list tab | Clicking on a specific topic card redirects the entire tab to the full list | 1. Log in to the Ihsan599 application. 2. Navigate to the header and click the "Bookmark" icon/tab. 3. Observe the list of recommended topic cards that appear. 4. Click on any one of the recommendation cards. | The tab reloads or redirects back to the full recommended list, without opening the specific selected topic. | The clicked card should open its associated content | Bug | Average | Video Link | Not Fixed
Bug_ID_026 | Profile menu | Change Password | Functional | New password auto-fills from current | Typing in the current password field auto-fills the new password field with the same value | 1. Go to Profile tab 2. Tap "Change Password" 3. Enter current password 4. Observe new password field | New password field auto-types same as current password | New password field should remain empty and allow custom input | Bug | Critical | Video Link | Not Fixed |  | Likely caused by input controller re-use or incorrect binding | 2025-06-02
Bug_ID_027 |  | Edit Profile | Functional | Name field accepts invalid input | Name input field accepts numbers, special characters, and empty input | 1. Log in to the ihsan599 app 2. Navigate to the Profile tab 3. Tap “Edit Profile” 4. Enter invalid characters (e.g., “123!@#”) into the Name field and save | Field accepts all values including numeric and symbols | Name field should only accept valid alphabetic characters and reject empty or invalid input | Bug | Minor | Screen Shot | Fixed |  | Input validation missing | 2025-06-06
Bug_ID_028 |  | Edit Profile>Server issue | Functional | Profile update fails via app | Name update fails through app but works via Postman API | 1. Open the ihsan599 application 2. Navigate to Profile tab 3. Tap "Edit Profile" 4. Change the name and save | "Failed to update profile" message appears | Name should update successfully and confirmation message shown | Bug | Major | Video Link | Not Fixed |  |  | 2025-06-06

## Test Cases
Test Result: | Passed | Failed | Need fix
| 3 | 3 | 0
Total: | 19
| Module | Test Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Bug Screenshot
TC_01 | Sign Up | Verify that sign up with valid cradential | 1. Open the app 2. Go to the Sign Up page. 3. Enter fillup all field. 4. Click on the Sign up button. | first name: Test last name: One Email: testone@gmaill password: 12345678 confirm password: 12345678 | Should be successfully registered | As Expected | Passed
TC_02 | Sign Up | Verify that sign up with invalid cradential | 1. Open the app 2. Go to the Sign Up page. 3. Enter fillup all field. 4. Click on the Sign up button. | first name: Test last name: One Email: testone@gmaill password: 12345678 confirm password: 12345612 | Should be error messages displayed | As Expected | Passed
TC_03 | Sign Up | Verify that registration with an already registered email address | 1. Open the app 2. Go to the Sign Up page. 3. Enter a name, password, and an email address that is already registered. 4. Click on the Sign up button. | first name: Test last name: One Email: testone@gmaill password: 12345678 confirm password: 12345678 | should not allow registration with an already registered email. | No As Expected | Passed
TC_04 | Sign Up | Verify that sign up with Google works from the Sign In page | 1. Open the app 2. Go to the Sign Up page. 3.Click on the Sign Up with Google button. | N/A | Should be signed up with Google successfully. | "Sign Up with Google" button triggers regular "Sign Up" action | Failed
TC_05 | Sign In | Verify that user sign in with valid credentials | 1. Open the app 2. Go to the Sign In page. 3. Enter password field. 4. Enter Confirm Password field. 5. Click on the Sign up button. | Email: testone@gmail.com password: 12345678 | Should be successfully logged in and redirected to the home page | No As Expected | Failed
TC_06 | Sign In | Verify that user sign in with invalid credentials | 1. Open the app 2. Click on the Sign In page. 3. Enter password field. 4. Enter Confirm Password field. 5. Click on the Sign up button. | Email: testone@gmail.com password: 12345612 | Should be displayed an error message "Invalid email or password" | No As Expected | Failed

## API Testing
Project name: |  | ihsan599
Tester |  | MD Abdur Rahaman Tutul
Testing Type: |  | API Testing
Test Case ExecutionTime: |  | 29.05.2025 to
Environment URL |  | https://8521-103-174-189-33.ngrok-free.app/api
Section | Users | Method | Request Type | End Point | Response | Status code | Status | Remarks
Authentication | users | POST | signup | {{ihsan}}/signup/ | Got proper response | 201 | OK
|  | POST | Verify OTP | {{ihsan}}/verify_otp/ | Got proper response | 200 | OK
|  | POST | Signup Resend OTP | {{ihsan}}/resend_otp/ | Got proper response | 200 | OK
|  | POST | Sign In | {{ihsan}}/signin/ | Got proper response | 200 | OK
|  | POST | Forget Password | {{ihsan}}/forgot_password/ | Got proper response | 200 | OK
|  | POST | Verify Reset password OTP | {{ihsan}}/verify_reset_otp/ | Got proper response | 200 | OK
|  | POST | Reset Resend OTP | {{ihsan}}/resend_otp/ | Got proper response | 200 | OK
|  | POST | Reset Password | {{ihsan}}/reset_password/ | Got proper response | 200 | OK
|  | POST | Logout | {{ihsan}}/logout/ | Got proper response | 200 | OK
Home | users | GET | Trending News Details | {{ihsan}}/home/trending_news/ | Got proper response | 200 | OK
|  | GET | Trending News | {{ihsan}}/home/trending_news/ | Got proper response | 200 | OK
|  | GET | Recommendation Topics | {{ihsan}}/home/recommended_topics/ | Got proper response | 200 | OK
|  | GET | Recommendation Topics Details | {{ihsan}}/home/recommended_topics/3/ | Got proper response | 200 | OK
|  | GET | Community Hub | {{ihsan}}/home/community_hub/ | Got proper response | 200 | OK
|  | GET | Search Results | {{ihsan}}/home/search_results/ | Bad Request | 400 | Bad Request | { "error": "Query parameter 'q' is required"}
|  | GET | Update Me | {{ihsan}}/home/update_me/ | Got proper response | 200 | OK
|  | GET | Posts | {{ihsan}}/home/update_me/ | Got proper response | 200 | OK
|  | GET | General Notifications | {{ihsan}}/notifications/general/ | Got proper response | 200 | OK
|  | GET | System Notifications | {{ihsan}}/notifications/system/